## 25.05.24
jkT; LoPN xaxk fe'ku&m0iz0
uekfe xaxs dk;Zdze esa vUrxZr fuekZ.kk/khu ifj;kstukvksa dh lkIrkfgd izxfr fooj.k
[19 empty] | 25.05.2024 |  |  |  |  | ¼#0 djksM+ essa½
dz-la- | ;kstuk dk uke | foRr iks"k.k | AA&ES and date |  |  |  |  | Agreement Cost |  |  | Date of completion |  |  |  | Previous Progress |  | Weekly Progress |  | Overall Progress |  | Centage (4%+4%) included in total Expenditure | Total Expenditure on work cost including O&M col.no17-col.no.17A) | Total Expenditure on O&M including electricity and diesel | Remarks
[15 empty] | Physical Progress | Financial Progress | Physical Progress | Financial Progress | Physical Progress | Financial Progress
|  |  | Sanction cost | Work Cost | Centage | O& M Cost ( 5/10/15 Years) | Sanction date | Capex | Opex | Total | Date of start as per agreement | As per AAES | As per Agreement | Extended date | Upto 18.05.2024 (Total) | Upto 18.05.2024 (Total) | 18.05.2024 to 25.05.2024 | 18.05.2024 to 25.05.2024 | Upto 25.05.2024 (Total) | Upto 25.05.2024 (Total)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  |  | 9 | 10 | 10 |  | 11 | 12 | 13 | 14 | 15 | 16 | 16A | 16 B | 16C | 17
iw.kZ ;kstuk,a
1 | lhojst ,.M ukWu lhojst ;kstuk] iz;kxjkt] fMfLVªDV&ch] bZ | ukWu bZ-,-ih- | 207.39 | 187.53 | 19.86 | 0 | 06.05.10/ 3.01.2019 | 118.2 | 0 | 118.2 | 27.4.2015 | Qjojh&2013 | ekpZ&2016 |  | iw.kZ | 175.48 | iw.kZ | 0 | iw.kZ | 175.48 | 19.18 | 156.3 | 0 | dk;Z iw.kZ
2 | lhojst ,.M ukWu lhojst ;kstuk] iz;kxjkt] fMfLVªDV&, | bZ-,-ih- | 97.95 | 97.95 | 0 | 0 | 06.05.10/ 3.01.2019 | 97.95 | 0 | 97.95 | 8.12.2010 | Qjojh&2013 | ekpZ&2016 |  | iw.kZ | 89.07 | iw.kZ | 0 | iw.kZ | 89.07 | 0 | 89.07 | 0 | dk;Z iw.kZ
3 | lhojst ;kstuk] fMfLVªDV&bZ] iz;kxjkt | bZ-,-ih- | 142 | 126.7 | 6.57 | 8.73 | 22.02.11 | 123.06 | 5.59 | 128.65 | 6.11.2011 | Qjojh&2013 | twu&2016 |  | iw.kZ | 138.25 | iw.kZ | 0 | iw.kZ | 138.25 | 6.57 | 131.68 | 5.06 | dk;Z iw.kZ
4 | 14 ,e-,y-Mh- ,l-Vh-ih- lyksjh] iz;kxjkt | bZ-,-ih- | 42.4 | 23.7706 | 1.9016 | 16.7246 | 27.11.13 | 24.25 | 29.15 | 53.4 | 6.12.2011 | Qjojh&2016 | flrEcj&2016 |  | iw.kZ | 34.93 | iw.kZ | 0 | iw.kZ | 34.93 | 1.9 | 33.03 | 8.76 | dk;Z iw.kZ]
5 | lhojst usVodZ fMfLVªDV&bZ] iz;kxjkt ¼vfr- dk;Z½ | bZ-,-ih- | 52.78 | 48.9 | 3.88 | 0 | 28.09.16 | 43.56 | 0 | 43.56 | 10.4.2017 | flrEcj&2016 | vçSy&2018 |  | iw.kZ | 50.43 | iw.kZ | 0 | iw.kZ | 50.43 | 3.71 | 46.72 | 0 | dk;Z iw.kZ
6 | lhojst ifj;kstuk] dUukSt | ukWu bZ-,-ih- | 43.66 | 38.37 | 3.03 | 2.26 | 24.02.11 | 39.65 | 0.75 | 40.4 | 20.09.2011 | vxLr&2012 | ekpZ&2018 |  | iw.kZ | 40.665 | iw.kZ | 0 | iw.kZ | 40.665 | 2.96 | 37.705 | 0.655 | dk;Z iw.kZ
7 | lhojst ;kstuk] ujksjk] cqqyUn'kgj | bZ-,-ih- | 48.45 | 39.73 | 2.26 | 6.46 | 04.03.14/ 09.05.2018 | 37.73 | 7.14 | 44.87 | 15.6.2015 | ebZ&2018 | ekpZ&2018 |  | iw.kZ | 44.23 | iw.kZ | 0 | iw.kZ | 44.23 | 2.26 | 41.97 | 1.2 | dk;Z iw.kZ
8 | lhojst ;kstuk] x<+eqDrs'oj | ukWu bZ-,-ih- | 46.51 | 40.68 | 3.25 | 2.58 | 24.02.11 | 32.71 | 1.75 | 34.46 | 7.9.2011 | vxLr&2013 | vçSy&2018 |  | iw.kZ | 45.44 | iw.kZ | 0 | iw.kZ | 45.44 | 3.22 | 42.22 | 0.37 | dk;Z iw.kZ
9 | lhojst vixzsMs'ku dk dk;Z] vuwi'kgj] cqyUn'kgj | bZ-,-ih- | 75.79 | 67.12 | 5.27 | 3.4 | 19.05.14 | 69.3 | 9.59 | 78.89 | 9.1.2016 | ebZ&2017 | flrEcj&2018 |  | iw.kZ | 70.82 | iw.kZ | 0 | iw.kZ | 70.82 | 5.13 | 65.69 | 3.29 | dk;Z iw.kZ
10 | lhojst ;kstuk] fMfLVªDV&lh] iz;kxjkt | bZ-,-ih- | 170.95 | 154.009 | 9.8685 | 7.0725 | 27.11.13/ 13.09.2019 | 147.58 | 7.92 | 155.5 | 07.4.2015 | flrEcj&2016 | vDVwcj&2018 | twu&2020 | iw.kZ | 177.19 | iw.kZ | 0 | iw.kZ | 177.19 | 9.86 | 167.33 | 7.15 | dk;Z iw.kZ
11 | lhojst ;kstuk] fMfLVªDV&ch] iz;kxjkt | bZ-,-ih- | 300.8425 | 278.2669 | 18.8158 | 3.7598 | 31.12.14/ 11.11.2019 | 276.65 | 4.2 | 280.85 | 25.6.2016 | fnlEcj&2017 | fnlEcj&2018 | twu&2020 | iw.kZ | 293.02 | iw.kZ | 0 | iw.kZ | 293.02 | 18.81 | 274.21 | 0.74 | dk;Z iw.kZ
12 | bUVjlsI'ku ,.M Mk;otZu ukyk] lhlkeÅ] dkuiqj | uekfe xaxs | 63.8 | 57.64 | 4.61 | 1.55 | 03.10.16 | 57.12 | 0 | 57.12 | 23.5.2017 | vçSy&2018 | vDVwcj&2018 |  | iw.kZ | 60.36 | iw.kZ | 0 | iw.kZ | 60.36 | 4.35 | 56.01 | 0 | dk;Z iw.kZA
13 | lhojst ;kstuk] fMfLVªDV&,] iz;kxjkt | bZ-,-ih- | 299.3956 | 269.1072 | 19.7504 | 10.538 | 20.02.14/ 11.11.2019 | 264.38 | 26.71 | 290.89 | 27.4.2015 | uoEcj&2017 | vçSy&2018 | twu&2020 | iw.kZ | 309.01 | iw.kZ | 0 | iw.kZ | 309.01 | 19.09 | 289.92 | 8.108 | dk;Z iw.kZA
14 | v;ks/;k uxj] tuin&v;ks/;k esa vkbZ ,.M Mh- ds fuekZ.k dk;Z | uekfe xaxs | 37.67 | 16.25 | 1.0955 | 20.32 | 11.06.18 | 11.58 | 17.44 | 29.02 | 17.11.2018 | uoEcj&2019 | fnlEcj&2019 |  | iw.kZ | 19.56 | iw.kZ | 0 | iw.kZ | 19.56 | 1.07 | 18.49 | 3.51 | dk;Z iw.kZA
15 | fcBwj uxj dkuiqj esa vkbZ-,.M Mh-,oa ,l-Vh-ih- ds dk;Z | uekfe xaxs | 13.4 | 10.25 | 0.7 | 2.45 | 10.10.17 | 9.88 | 1.87 | 11.75 | 20.9.2018 | vçSy&2018 | fnlEcj&2019 |  | iw.kZ | 10.87 | iw.kZ | 0 | iw.kZ | 10.87 | 0.7 | 10.17 | 0.15 | dk;Z iw.kZA
16 | o`Unkou] eFkqjk esa uohuhdj.k ,oa mPphdj.k dk dk;Z | uekfe xaxs | 42.82 | 26.74 | 1.19 | 14.89 | 29.03.17 / 07.05.18/ 11.12.2019 | 18.61 | 14.89 | 33.5 | 1.12.2018 | ekpZ&2018 | Qjojh&2020 |  | iw.kZ | 22.49 | iw.kZ | 0 | iw.kZ | 22.49 | 1.17 | 21.32 | 4.61 | dk;Z iw.kZA
17 | lhojst ;kstuk lhojst fMfLVªDV&1] dkuiqj | bZ-,-ih- | 430.49 | 395.2 | 23.81 | 11.48 | 18.10.16/ 10.12.2019 | 389.83 | 11.48 | 401.31 | 17.8.2017 | tqykbZ&2020 | vxLr&2020 | fnlEcj&2020 | iw.kZ | 418.99 | iw.kZ | 0 | iw.kZ | 418.99 | 23.81 | 395.18 | 6.82 | dk;Z iw.kZA( Expenditure including Price Escalation Rs.46.11 cr)
18 | jeuk ojk.klh esa 50,e-,y-Mh-{kerk ds ,l-Vh-ih- dk fuekZ.k ,oa j[k&j[kko dk dk;ZA ¼HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 161.31 | 102 | 8.16 | 51.15 | 23.12.2016/21.09.2017 | 102 | 59.31 | 161.31 | 19.02.2018 | fnlEcj&2019 | uoEcj&2019 | fnlEcj&2020 | iw.kZ | 133.08 | iw.kZ | 0 | iw.kZ | 133.08 | 7.53 | 125.55 | 5.95 | dk;Z iw.kZA (Expenditure Including NMCG+ SPV release)
19 | jkeuxj]okjk.klh esa vkbZ-,.M Mh-,oa ,l-Vh-ih-ds dk;Z | uekfe xaxs | 72.91 | 23.88 | 1.75 | 47.28 | 28.07.17 | 22.13 | 47.28 | 69.41 | 1.12.2018 | fnlEcj&2019 | vxLr&2020 | fnlEcj&2020 | iw.kZ | 27.57 | iw.kZ | 0 | iw.kZ | 27.57 | 1.71 | 25.86 | 0 | dk;Z iw.kZA
20 | iz;kxjkt uxj ds fufeZr ,l-Vh-ih- ds iquZjks)kj rFkk 15 o"kZ dk j[k&j[kko ¼ HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 904 | 58.15 | 0 | 845.85 | 09.03.18 | 170.41 | 387.18 | 557.59 | 16.09.2019 | ekpZ&2020 | flrEcj&2021 |  | iw.kZ | 281.02 | iw.kZ | 0 | iw.kZ | 281.02 | 0 | 281.02 | 92.13 | dk;Z iw.kZA (Expenditure Including NMCG+ SPV release)
21 | pqukj uxj esa fQdy Lyt eSustesUV dk dk;Z | uekfe xaxs | 2.7 | 2.1556 | 0.069 | 0.48 | 07.03.2019 | 1.8 | 0.244 | 2.044 | 9.11.2019 | ekpZ&2020 | flrEcj&2020 | uoEcj&2020 | iw.kZ | 2.16 | iw.kZ | 0 | iw.kZ | 2.16 | 0.07 | 2.09 | 0.06 | dk;Z iw.kZA
22 | fQjkstkckn uxj] esa vkbZ ,.M Mh- ds dk;Z | uekfe xaxs | 51.08 | 23.92 | 1.635 | 25.53 | 01.03.2019 | 18.88 | 23.54 | 42.42 | 14.11.2019 | flrEcj&2020 | uoEcj&2020 | vxLr&2021 | iw.kZ | 27.79 | iw.kZ | 0 | iw.kZ | 27.79 | 1.52 | 26.27 | 3.62 | dk;Z iw.kZA
23 | jkexaxk lhojst ifj;kstuk] eqjknkckn | ukWu EAP | 330.05 | 278.85 | 19.03 | 32.17 | 24.02.11/ 31.07.2020 | 268.02 | 9 | 277.02 | 21.10.2011 | Qjojh&2014 | vçSy&2013 | fnlEcj&2021 | iw.kZ | 301.53 | iw.kZ | 0 | iw.kZ | 301.53 | 18.22 | 283.31 | 22.43 | dk;Z iw.kZA
24 | dklxat uxj] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z | uekfe xaxs | 76.73 | 36.6 | 2.49 | 37.64 | 24.12.2018 | 34.24 | 33.32 | 67.56 | 5.7.2019 | fnlEcj&2020 | tqykbZ&2021 | ekpZ&2022 | iw.kZ | 40.7 | iw.kZ | 0 | iw.kZ | 40.7 | 2.43 | 38.27 | 1.79 | dk;Z iw.kZA
25 | bVkok uxj] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z | uekfe xaxs | 140.6 | 56.86 | 3.89 | 79.85 | 28.02.2019 | 47.6 | 75.27 | 122.87 | 22.7.2019 | vDVwcj&2020 | tuojh&2021 | ebZ&2022 | iw.kZ | 54.47 | iw.kZ | 0 | iw.kZ | 54.47 | 3.44 | 51.03 | 2.67 | dk;Z iw.kZA
26 | eFkqjk uxj esa vkbZ-,.M Mh- ,oa ,l-Vh-ih- ds dk;Z dk iqujks)kj ,oa {kerk mPphdj.k dk dk;Z ¼HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 460.45 | 264.4 | 8.78 | 187.27 | 11.06.18 | 250.67 | 187.28 | 437.95 | 15.1.2019 | twu&2020 | tuojh&2021 | twu&2022 | iw.kZ | 315.3 | iw.kZ | 0 | iw.kZ | 315.3 | 8.78 | 306.52 | 16.7 | dk;Z iw.kZA (Expenditure Including NMCG+ SPV release)
27 | tk;dk lgk;frr lhojst ;kstuk] okjk.klh | tk;dk | 659.62 | 633.41 | 26.21 | 0 | 14.07.10/ 23.07.2020 | 447.76 | 0 | 447.76 | 10.1.2013 | tqykbZ&2015 | ebZ&2017 | twu&2022 | iw.kZ | 597.67 | iw.kZ | 0 | iw.kZ | 597.67 | 26.21 | 571.46 | 0 | dk;Z iw.kZA ¼;kstuk esa ukWu lhojst dEiksUksUV dks O;; lfEefyr djrs gq,A
28 | ckxir uxj] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z | uekfe xaxs | 77.36 | 38.72 | 2.6616 | 35.98 | 19.02.2019 | 27.15 | 36.42 | 63.57 | 8.01.2020 | Qjojh&21 | vçSy&2021 | flrEcj&2022 | iw.kZ | 32.42 | iw.kZ | 0 | iw.kZ | 32.42 | 2.12 | 30.3 | 0.39 | dk;Z iw.kZA
29 | uSuh] QkQkeÅ ,oa >wlh {ks= iz;kxjkt esa vkbZ-,.M Mh ,oa ,l-Vh-ih- ds dk;Z ¼ HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 767.6 | 280.14 | 21.67 | 465.79 | 19.05.17 | 229.09 | 121.49 | 350.58 | 16.09.2019 | ebZ&2020 | flrEcj&2021 | ebZ&2023 | iw.kZ | 276.97 | iw.kZ | 0 | iw.kZ | 276.97 | 18.43 | 258.54 | 0 | STPs are Under Trial-run
30 | tkSuiqj uxj] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z | uekfe xaxs | 206.05 | 132.89 | 9.2536 | 63.91 | 12.02.2019 | 118.67 | 45.32 | 163.99 | 21.10.2019 | Qjojh&2021 | vDVwcj&2021 | twu&2023 | iw.kZ | 146.78 | iw.kZ | 0 | iw.kZ | 146.78 | 8.62 | 138.16 | 0 | dk;Z iw.kZA
31 | cqM+kuk uxj] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z ¼ HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 48.76 | 25.1 | 1.7 | 21.96 | 18.02.2019 | 29.75 | 11.53 | 41.28 | 04.06.2021 | Qjojh&2021 | twu&2023 |  | iw.kZ | 29.15 | iw.kZ | 0 | iw.kZ | 29.15 | 1.23 | 27.92 | 0 | STP has commissioned on 27.06.2023. All 3 drain are tapped.
32 | dkuiqj uxj fufeZr ,l-Vh-ih- ds iqujks)kj] iu[kk esa vkbZ ,.M Mh- ,l-Vh-ih- dk fuekZ.k rFkk 15 o"kksaZ dk j[k&j[kko ¼HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 967.23 | 248.39 | 0 | 718.84 | 12.03.18 | 195.93 | 512.77 | 708.7 | 11.10.2019 | ekpZ&2020 | vDVwcj&2021 | uoEcj&2023 | 99% | 254.98 | 0% | 0 | 99% | 254.98 | 0 | 254.98 | 38.949 | Panka STP has been commissioned and I&D works have also been completed. Balance works of CCT and TEPH at Jajmau STP is in progress . It will be completed by Apr-2024.
mi;ksx |  |  | 7042.7481 | 4083.6793 | 233.161 | 2725.9149 |  | 3726.14 | 1688.434 | 5414.374 | [5 empty] | 4522.395 |  | 0 |  | 4522.395 | 224.1 | 4298.295 | 235.112
izxfr esa py jgh ;kstuk,a
33 | 'kqDykxat] mUuko esa vkbZ-,.M Mh- ,oa ,l-Vh-ih- ds dk;Z ¼ HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 65.18 | 25.93 | 1.9 | 37.35 | 28.07.17 | 21.29 | 17.58 | 38.87 | 11.10..2019 | Qjojh&2020 | fnlEcj&2022 | fnlEcj&2023 | 81% | 23.47 | 0% | 0 | 81% | 23.47 | 1.4 | 22.07 | 0 | dk;Z izxfr ijA (Expenditure Including NMCG+ SPV release)
34 | mUuko uxj esa vkbZ-,.M Mh- ,oa ,l-Vh-ih- ds dk;Z ¼ HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 102.2 | 43.73 | 3.22 | 55.25 | 28.07.17 | 38.27 | 30.4 | 68.67 | 11.10.2019 | viSzy&2020 | vDVwcj&2021 | uoEcj&2023 | 95.5% | 52.01 | 0% | 0 | 95.5% | 52.01 | 2.9 | 49.11 | 0 | STP has been commissioned. Due to delay in work of desilting of gravity main line it was proposed to lay about 323 m of diversion line for taking drain discharge into STP. MS pipe has been procured . Work of diversion line has started.
35 | lqYrkuiqj uxj] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z | uekfe xaxs | 70.18 | 43.6778 | 2.5922 | 23.91 | 04.12.2019 | 40.88 | 26.71 | 67.59 | 24.12.2018 / 04.12.2019 | fnlEcj&2020 | uoEcj&2021 | uoEcj&2023 | 99.8% | 43.91 | 0% | 0 | 99.8% | 43.91 | 2.39 | 41.52 |  | 2 STPs of capacity 5 MLD and 10 MLD have been commissioned. 2 MLD STP Has been Started..
36 | eqTtQj uxj] ds lhojst ;kstukvksa ds iqujks)kj dk dk;Z ¼ HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 234.03 | 108.32 | 7.33 | 118.38 | 02.01.2019 | 146.25 | 58.84 | 205.09 | 04.06.2021 | tuojh&2021 | twu&2023 | fnlEcj&2023 | 93.98% | 141.79 | 0.21% | 0 | 94.19% | 141.79 | 4.72 | 137.07 | 0 | 22.00 MLD STP at Sahawali commissioned on 07.06.2023. 32.5 MLD STP at Kidwai nagar work is in progress and it will be completed by Apr-24.
37 | eqjknkckn uxj] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z ¼HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 118.69 | 53.53 | 3.52 | 61.64 | 23.07.18 | 79.6 | 33.68 | 113.28 | 20.1.2023 | tqykbZ&2020 | tuojh&2025 |  | 62% | 35.56 | 1% | 0 | 63% | 35.56 | 1.76 | 33.8 | 0 | dk;Z izxfr ijA
38 | y[kuÅ uxj] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z | uekfe xaxs | 213.91 | 101.31 | 6.97 | 105.63 | 02.03.2019/ 06.05.2020 | 100.95 | 73.97 | 174.92 | 01.06.2022 | ekpZ&2021 | uoEcj&2023 |  | 80.42% | 94.86 | 0.25% | 0 | 80.67% | 94.86 | 3.72 | 91.14 | 0 | dk;Z izxfr ijA
39 | xkthiqj esa vkbZ-,.M Mh- ,oa ,l-Vh-ih- ds dk;Z ¼ HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 152.83 | 53.5973 | 3.0627 | 96.17 | 16.11.2017 / 06.05.2020 | 68.65 | 72.29 | 140.94 | 10.04.2022 | fnlEcj&2019 | tuojh&2024 |  | 98.5% | 69.27 | 0% | 0 | 98.5% | 69.27 | 1.53 | 67.74 | 0 | dk;Z izxfr ijA (Expenditure Including NMCG+ SPV release)
40 | fetkZiqj esa vkbZ-,.M Mh- ,oa ,l-Vh-ih- ds dk;Z ¼ HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 129.08 | 51.9825 | 4.04 | 73.05 | 14.11.2017/ 28.05.2020 | 75.3 | 76.28 | 151.58 | 10.04.2022 | Qjojh&2020 | tuojh&2024 |  | 99% | 74.36 | 0% | 0 | 99% | 74.36 | 1.8 | 72.56 | 0 | dk;Z izxfr ijA (Expenditure Including NMCG+ SPV release)
41 | cjsyh uxj] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z ¼ HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 271.39 | 139.44 | 10.7 | 121.25 | 03.01.2019 | 182 | 51.72 | 233.72 | 31.08.2022 | tuojh&2021 | vxLr&2024 |  | 99% | 181.03 | 0% | 0 | 99% | 181.03 | 5.35 | 175.68 | 0 | dk;Z izxfr ijA (Expenditure Including NMCG+ SPV release)
42 | tuin 'kkeyh esa dSjkuk uxj] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z | uekfe xaxs | 78.42 | 37.28 | 2.63 | 38.51 | 07.12.2020 | 27.79 | 31.4 | 59.19 | 28.08.21 | fnlEcj&2022 | ebZ&2023 | fnlEcj&2023 | 94.01% | 29.09 | 0.57% | 0 | 94.58% | 29.09 | 1.88 | 27.21 | 0 | dk;Z izxfr ijA
43 | Q:Z[kkckn&Qrsgx<+ esa vkbZ-,.M Mh- ,oa ,l-Vh-ih- ds dk;Z ¼ HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 261.12 | 181.73 | 6.98 | 72.41 | 16.10.17/ 12.01.2021 | 180 | 72.41 | 252.41 | 24.06.2022 | vDVwcj &2019 | twu&2024 |  | 88% | 177.62 | 0.3% | 0 | 88.3% | 177.62 | 3.49 | 174.13 | 0 | dk;Z izxfr ijA (Expenditure Including NMCG+ SPV release)
44 | QStkckn uxj] tuin &v;ks/;k ] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z ¼HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 221.66 | 109.03 | 7.62 | 105.01 | 06.05.2021 | 100 | 49.47 | 149.47 | 03.03.2022 | ekpZ&2023 | ekpZ&2024 |  | 87.13% | 58.42 | 1.37% | 0 | 88.5% | 58.42 | 3.81 | 54.61 | 0 | dk;Z izxfr ijA
45 | vkxjk uxj] ds lhojst ;kstukvksa ds iqujks)kj ,oa 15 Zo"kksZa dk j[kj[kko ds dk;Z ¼ HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 842.25 | 371.29 | 25.4 | 445.56 | 24.12.2018/ 06.05.2020 | 375 | 207.85 | 582.85 | 05.04.2023 | viSzy&2023 | viSzy&2025 |  | 40.42% | 124.45 | 1.28% | 0 | 41.7% | 124.45 | 12.7 | 111.75 | 0 | dk;Z izxfr ijA
46 | iz;kxjkt uxj esa 13 ux ukyksa ds vkbZ ,.M Mh ,oa lyksjh ,l0Vh0ih0 dh 43 ,e0,y0Mh0 {kerk o`f) ds dk;Z | uekfe xaxs | 331.75 | 180.27 | 11.22 | 140.26 | 14.03.23 | 111.86 | 92.54 | 204.4 | 19.03.2024 | vxLr&2024 | vxLr&2025 |  | 0% | 4.74 | 0% | 0 | 0% | 4.74 | 5.61 | -0.87 | 0 | Date of Start is given as 19.03.24. Survey Work is in Progress.
47 | vLlh&ch-,p-;w- {ks= ¼Qst+&AA½] okjk.klh esa ,l-Vh-ih- dk dk;Z | uekfe xaxs | 308.09 | 116.46 | 7.8 | 183.83 | 19.10.2022 | 86.46 | 65.1 | 151.56 | 07.03.2024 | tqykbZ&2024 | fnlEcj&2025 |  | 2.5% | 4.32 | 0% | 0 | 2.5% | 4.32 | 3.9 | 0.42 | 0 | Date of start is given as 07.03.24. Soil Testing is in Progress.
mi;ksx |  |  | 3400.78 | 1617.5776 | 104.9849 | 1678.21 |  | 1634.3 | 960.24 | 2594.54 | [5 empty] | 1114.9 |  | 0 |  | 1114.9 | 56.96 | 1057.94 | 0
VsUMj izfd;k esa py jgh ;kstuk,a
48 | esjB uxj] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z ¼HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 690.71 | 384.21 | 26.31 | 280.19 | 19.02.2019/ 06.05.2020 | 356.95 | 12.79 | 369.74 |  |  |  |  | 0% | 13.34 | 0% | 0 | 0% | 13.34 | 13.34 | 0 | 0 | LOA issued to (JV) M/s GA Infra Private Ltd, Rajasthan and, M/s SSG Infratech Pvt. Ltd. New Delhi on 27.05.2023. Concessionaire agreement signed is signed on 05.09.23. Financial closure is under process. Financial closure document sent to NMCG on 15.03.24 for review.
49 | lgkjuiqj uxj] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z ¼HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 577.23 | 266.34 | 20.55 | 290.34 | 15.06.2022 | [7 empty] | 0% | 10.27 | 0% | 0 | 0% | 10.27 | 10.27 | 0 | 0 | Technical bids were opened on 23.03.2023. 6 bids were received which have been evaluated. Observations were received from NMCG over the TBER . Revised TBEC report sent to NMCG on 02.08.23. NOC received from NMCG for opening of Financial bid on 28.12.23 Financial bid has been opened on 12.01.24 which is under evaluation.
50 | eFkqjk uxj esa vo'ks"k ukyksa ds vkbZ-,.M Mh- ,oa ,l-Vh-ih- ds dk;Z dk iqujks)kj ,oa {kerk mPphdj.k dk dk;Z ¼HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 292.56 | 149.85 | 9.61 | 133.1 | 07.09.2022 | 194.7 | 45.31 | 240.01 |  |  |  |  | 0% | 4.805 | 0% | 0 | 0% | 4.805 | 4.805 | 0 | 0 | LOA issued to JV M/s Enviro Infra engineer Limited, Dehli and M/s Micro Transmission System , greater Noida. on 27.09.23. financial closer is under process. Concessionaire agreement signed is signed on 12.12.23. Financial closure is under process.
51 | Nkrk uxj] tuin eFkqjk] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z | uekfe xaxs | 56.15 | 34.52 | 2.22 | 19.41 | 25.10.2022 | [8 empty] | 1.11 |  |  |  | 1.11 | 1.11 | 0 |  | Technical bids were opened on 26.06.2023. 2 bids were received. Technical bid evaluation report sent to NMCG on 14.08.2023. NOC received from NMCG for Re-tendering of project on 12.10.23. Re-bid is invited on 12.12.2023. 05 bid received. Technical bid evaluation report sent to NMCG on 12.01.24. NOC received from NMCG for opening of Financial bid on 07.03.24.Financial bid opened on 18.03.24. which is under evaluation.
52 | dkslkhdyk uxj] tuin eFkqjk] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z | uekfe xaxs | 66.59 | 31.23 | 2.03 | 33.33 | 25.10.2022 | [8 empty] | 1.015 |  |  |  | 1.015 | 1.015 | 0 |  | Technical bids were opened on 26.06.2023. 9 bids were received . Technical bid evaluation report sent to NMCG on 14.08.2023.Financial bid evaluation report sent to NMCG on 13.12.23. NOC received from NMCG for issuing of LOA on 20.02.24 to L2 bidder Reply for same sent to NMCG on 27.02.24 for reconsideration of UPJN recommendation as previous.
53 | o`Unkou] uxj] tuin eFkqjk] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z | uekfe xaxs | 77.7 | 39.9 | 2.56 | 35.24 | 25.10.2022 | [8 empty] | 1.28 |  |  |  | 1.28 | 1.28 | 0 |  | Technical bids were opened on 26.06.2023. 6 bids were received . Financial bid evaluation report sent to NMCG on 05.12.23. NOC received from NMCG fot issuing of LOA on 08.03.24.LOA is issued to L1 bidder on 15.03.24
54 | iz;kxjkt uxj esa 07 ux ukyksa ds vkbZ ,.M Mh ,oa jktkiqj ,l0Vh0ih0 dh 90 ,e0,y0Mh0 {kerk o`f) ds dk;Z | uekfe xaxs | 475.98 | 242.85 | 15.24 | 217.89 | 27.01.2023 | [8 empty] | 7.62 |  |  |  | 7.62 | 7.62 | 0 |  | Technical bids were opened on 08.06.2023. 8 bids have been received . Technical bid evaluation report sent to NMCG on 10.08.2023. NOC received from NMCG for opening of Financial bid on 01.11.23. . Financial bid evaluation report sent to NMCG on 13.12.23. NMCG has given its comment on evaluation report on 30.01.24 with change in ranking of bidder. Reply for same sent to NMCG
55 | y[kuÅ uxj] Qst&2 ikV&1 esa 03 ux ukyksa ds vkbZ ,.M Mh ,oa 50 ,e0,y0Mh0 ,l0Vh0ih0 ds dk;Z | uekfe xaxs | 264.67 | 137.55 | 8.52 | 118.6 | 30.01.2023 | [8 empty] | 4.26 |  |  |  | 4.26 | 4.26 | 0 |  | Technical bids were opened on 22.06.2023. 8 bids were received . Technical bid evaluation report sent to NMCG on 04.08.23. NOC received from NMCG for opening of Financial bid on 19.12.23.Financial bid evaluation report sent to NMCG on 11.01.24. NOC received from NMCG for issuance of LOA to L1 bidder on 15.03.24.
56 | gkFkjl uxj esa 10 ux ukyksa ds vkbZ ,.M Mh ,oa 24 ,e0,y0Mh0 ,l0Vh0ih0 ds dk;Z | uekfe xaxs | 128.91 | 70.47 | 4.55 | 53.88 | 30.01.2023 | [8 empty] | 2.275 |  |  |  | 2.275 | 2.275 | 0 |  | Financial bid evaluation report sent to NMCG on 12.01.24. NOC received from NMCG for issuing of LOA on 20.02.24 to L2 bidder. Reply for same sent to NMCG on 27.02.24. for annulling the bidding process.
57 | tuin 'kkeyh esa cur uxj] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z | uekfe xaxs | 48.71 | 24.93 | 1.58 | 22.2 | 25.05.23 | [8 empty] | 0.79 |  |  |  | 0.79 | 0.79 | 0 |  | NIT is published on 09.08.23. Last date for bid Submission is 09.11.23. Technical bid opened on 10.11.23. 04 bid received only 01 bid is responsive so bid is invited again. Last date of bid submission is 22.02.2024. 09 bid received which is under evaluation.Tender Sanctioning Committee Meeting held on 23.04.2024 for evaluation of technical bid.Technical evaluation Report sent to NMCG on dt. 06.05.2024 .
58 | tuin 'kkeyh esa 'kkeyh uxj] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z | uekfe xaxs | 206.02 | 103.19 | 6.66 | 96.17 | 25.05.23 | [8 empty] | 3.33 |  |  |  | 3.33 | 3.33 | 0 |  | NIT is published on 09.08.23. Last date for bid Submission is 09.11.23. Technical bid opened on 10.11.23. Technical bid evaluation report sent to NMCG on 21.12.2023.NOC received from NMCG for opening of financial bid on 12.01.24. Financial evaluation report sent to NMCG on 03.04.2024.
59 | tuin 'kkeyh esa cUrh [ksM+k xzke] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z | uekfe xaxs | 55.47 | 29.41 | 1.84 | 24.22 | 25.05.23 | [8 empty] | 0.92 |  |  |  | 0.92 | 0.92 | 0 |  | NIT is published on 09.08.23. Last date for bid Submission is 09.11.23. Technical bid opened on 10.11.23. 04 bid received only 01 bid is responsive so bid is invited again. . Last date of bid submission is 26.02.2024. 07 Bid received which is under evaluation. Tender Sanctioning Committee Meeting held on 23.04.2024 for evaluation of technical bid.Technical evaluation Report sent to NMCG on dt. 06.05.2024
60 | tuin 'kkeyh esa Fkkuk Hkou uxj] esa vkbZ ,.M Mh- ,oa ,l-Vh-ih- ds dk;Z | uekfe xaxs | 97.19 | 55.63 | 3.5 | 38.06 | 25.05.23 | [8 empty] | 1.75 |  |  |  | 1.75 | 1.75 | 0 |  | NIT is published on 09.08.23. Last date for bid Submission is 09.11.23. Technical bid opened on 10.11.23. 04 bid received only 01 bid is responsive so bid is invited again. . Last date of bid submission is 22.02.2024. 07 bid received which is under evaluation.Tender Sanctioning Committee Meeting held on 23.04.2024 for evaluation of technical bid.Technical evaluation Report sent to NMCG on dt. 06.05.2024
61 | iz;kxjkt uxj esa 02 ux ukyksa ds vkbZ ,.M Mh ,oa uSuh ,l0Vh0ih0 dh 50 ,e0,y0Mh0 {kerk o`f) ds dk;Z | uekfe xaxs | 186.47 | 83.71 | 5.44 | 97.32 | 05.09.23 | [8 empty] | 2.72 |  |  |  | 2.72 | 2.72 | 0 |  | NIT is published on 06.12.23. Last date of bid submission is 26.02.24. 14 bid received which is under evaluation.
62 | gkiqM+ uxj] esa 01 ux ukyksa ds vkbZ ,.M Mh ,oa 06 ,e0,y0Mh0 ,l0Vh0ih0 ds dk;Z | uekfe xaxs | 49.06 | 22.85 | 1.42 | 24.79 | 05.09.23 | [8 empty] | 0.71 |  |  |  | 0.71 | 0.71 | 0 |  | NIT is published on 01.12.23. Last date of bid submission is 17.03.2024.. 02 bid received which is under evaluation.
63 | y[kuÅ uxj] Qst&2 ikV&2 esa 01 ux ukyksa ds vkbZ ,.M Mh ,oa 100 ,e0,y0Mh0 ,l0Vh0ih0 ds dk;Z ¼HAM ih-ih-ih- vk/kkfjr½ | uekfe xaxs | 351.03 | 207.99 | 13.14 | 129.9 | 19.09.23 | [8 empty] | 6.57 |  |  |  | 6.57 | 6.57 | 0 |  | NIT is published on 29.11.23. Last date of bid submission is 22.04.24. 15 bid received which is under evaluation.
mi;ksx |  |  | 3624.45 | 1884.63 | 125.17 | 1614.64 | [9 empty] | 62.765 |  | 0 |  | 62.765 | 62.765 | 0 | 0
dqy ;ksx |  |  | 14067.9781 | 7585.8869 | 463.3159 | 6018.7649 |  | 5360.44 | 2648.674 | 8008.914 | [5 empty] | 5700.06 |  | 0 |  | 5700.06 | 343.825 | 5356.235 | 235.112